## Sheet1
SR. No	Module	Sub-Module	Test Cases/ Test Jobs	Test Steps	Planned No of days	Revised. No of Days	Original Dates	Expected Results	Actual Results	Pass / Fail	Completion Date	Revised Original Dates	Revised / Completion Date	Status	Remarks	Queries (Filename)	Done By BSG/IT	Designed By	Executed By
1	Login	Login	To Verify ETB Customer Mobile Number.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter ETB Customer Mobile Number linked to Bank Account Number.			8-01-2024	System allows user to show and use Mobile Number Field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
2	Login	Login	To Validate ETB Customer Mobile Number Field.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Invalid Values or Keep Field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
3	Login	Login	To Verify Captcha Field should be visible and Clickable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed.			8-01-2024	Captcha Field should be visible and Clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
4	Login	Login	To Verify that ‘Reload’ Captcha button should be visible and Clickable.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed.5.Enter Invalid Captcha Values or Keep field Blank.			8-01-2024	‘Reload’ Captcha button should be visible and Clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
5	Login	Login	To Verify new captcha should be visible after clicking on ‘Reload’ button	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed.5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down 11.Click on ‘I Agree’ Button 12.Select Checkbox to Accept Terms and Conditions.13. Scroll Down 14. Click on ‘I Agree’ Button			8-01-2024	Reload button should be clickable and new Captcha should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
6	Login	Login	Verify that Invalid captcha should not be accepted	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Invalid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down 11.Click on ‘I Agree’ Button 12.Select Checkbox to Accept Terms and Conditions.13. Scroll Down 14. Click on ‘I Agree’ Button 15. Click on ‘Receive OTP’			8-01-2024	Invalid captcha should not be accepted and Error Message Should be Shown. / “Please enter the captcha”	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
7	Login	Login	To Verify, ‘KCC/Agri” Service should be visible and clickable.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service			8-01-2024	‘KCC/Agri” Service should be visible and clicable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
8	Login	Login	To Verify ‘I Agree’ Button should be disabled.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service			8-01-2024	I Agree Button should be Disabled	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
9	Login	Login	To verify ‘I Agree’ Button should be enabled and Clickable.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.			8-01-2024	I Agree Button should be Enabled	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
10	Login	Login	To Verify, Banking Products and services check box should be visible and clickable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.			8-01-2024	Banking Products and services check box should be visible and clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
11	Login	Login	To Verify ‘I Agree’ Button should be disabled.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.			8-01-2024	‘I Agree’ Button should be disabled.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
12	Login	Login	To verify ‘I Agree’ Button should be enabled and Clickable.	1.Open Dairy Loan URL in Browser.2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down. 11.Click on ‘I Agree’ Button			8-01-2024	System Allows user to Navigate to Enter OTP Page will be Displayed. With Below details. - 6 Digit OTP Fields. - Resend OTP Button, - 30 Sec Timer, - Submit Button	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
13	Login	Login	To Verify Terms & Conditions should be visible and clickable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down 11.Click on ‘I Agree’ Button 12.Select Checkbox to Accept Terms and Conditions.			8-01-2024	Terms & Conditions should be visible and clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
14	Login	Login	To Verify ‘I Agree’ Button should be disabled.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down 11.Click on ‘I Agree’ Button 12.Select Checkbox to Accept Terms and Conditions.			8-01-2024	‘I Agree’ Button should be disabled.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
15	Login	Login	To verify ‘I Agree’ Button should be enabled and Clickable.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down 11.Click on ‘I Agree’ Button 12.Select Checkbox to Accept Terms and Conditions.13. Scroll Down 14. Click on ‘I Agree’ Button			8-01-2024	‘I Agree’ Button should be enabled and Clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
16	Login	Login	To Verify that ‘Important Links’ hyperlink text should be visible and clickable.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3. Click on ‘Important Links’ hyperlink text			8-01-2024	‘Important Links’ hyperlink text should be visible and clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
17	Login	Login	To Verify, Receive OTP Button.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Mobile Number. 4.Captcha field will be displayed. 5.Enter Valid Captcha Values. 6.Select Check box‘KCC/Agri” Service7. Scroll Down 8. Click on ‘I Agree’ Button.9.Select Checkbox Banking Products and services.|10.Scroll Down 11.Click on ‘I Agree’ Button12.Select Checkbox to Accept Terms and Conditions.13. Scroll Down 14. Click on ‘I Agree’ Button 15.Click on Receive OTP button.			8-01-2024	Receive OTP button should be clickable and user should receive OTP	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
18	Login	Login	To Verify that Receive OTP Button should be Disable if Any field is blank or invalid data is entered.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter invalid Values in All fields and Click on Receive OTP button.			8-01-2024	Receive OTP Button should not be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
19	Login	Login	To Verify, Receive OTP Button.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button.			8-01-2024	Receive OTP button should be clickable and user should receive OTP	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
20	Login	Login	To Verify Note:Document List.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button.4.Note:Document List : *HDFC Debit Card & PIN *Land Survey No			8-01-2024	“Keep the following Documents handy” / *HDFC Debit Card & PIN / *Land Survey No Should be Visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
21	Login	Login	To Verify, OTP Screen.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter OTP Screen will Open.			8-01-2024	OTP screen should be open	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
22	Login	Login	To Validate, OTP Screen.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter Invalid OTP Values.			8-01-2024	Invalid OTP should not be accepted and Error message should be shown.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
23	Login	Login	To Verify, Resend OTP.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Click on Resend OTP.			8-01-2024	Receive OTP button should be clickable and user should be navigate to next page.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
24	LOS	Loan Requirement Details	To Verify, Pre -approved Cattle Loan Details.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter Valid OTP to Login. 5.Linked account list will be displayed.6.Select One Account and Click on Accept Button. 7.Pre -approved Cattle Loan Details will be displayed.			8-01-2024	If account is not linked,Pre -approved Cattle Loan Details should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
25	LOS	Loan Requirement Details	To Verify, Accept Button.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter Valid OTP to Login.5.Linked account list will be displayed.6.Select One Account and Click on Accept Button. 7.Pre -approved Cattle Loan Details will be displayed. 8.Click on Accept Button.			8-01-2024	Accept button should be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
26	LOS	Loan Requirement Details	To Verify, I’ll do it later Button	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter Valid OTP to Login. 5.Linked account list will be displayed.6.Select One Account and Click on Accept Button.7.Pre -approved Cattle Loan Details will be displayed. 8.Click on I ‘ll do it later Button.			8-01-2024	“I ‘ll do it later” hyperlink text should be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
27	LOS	Loan Requirement Details	To Verify, if Clicked on Yes	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on I ‘ll do it later Button. 6.Pop-up will be generated Click on Yes.			8-01-2024	Journey will stop and User will logged out	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
28	LOS	Loan Requirement Details	To Verify, if Clicked on No.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on I ‘ll do it later Button. 6.Pop-up will be generated Click on No.			8-01-2024	Pop up will get close.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
29	LOS	Loan Requirement Details	To Verify, Linked Accounts Connected to mobile Number	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter Valid OTP to Login. 5.Linked account list will be displayed.			8-01-2024	Linked Accounts will be visible	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
30	LOS	Loan Requirement Details	To Verify, ‘Accept’ Button.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Enter Valid Values in All fields and Click on Receive OTP button. 4.Enter Valid OTP to Login. 5.Linked account list will be displayed.6.Select One Account and Click on Accept Button.			8-01-2024	Accept button should be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
31	LOS	Loan Requirement Details	To Verify, Loan Requirement Page	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open.			8-01-2024	User should be navigate to loan requirement page	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
32	LOS	Loan Requirement Details	To Verify, Dairy Society Name	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name 8.Harit Pradesh Milk Producer Company Ltd. Should be pre selected			8-01-2024	Society name should be pre selected.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
33	LOS	Loan Requirement Details	To Verify Cattle Required, ‘Type’ field Should Visible and Clickable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name8.Select Harit Pradesh Milk Producer Company Ltd.9.Click on Type field.			8-01-2024	‘Type’ field Should Visible and Clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
34	LOS	Loan Requirement Details	To Verify Selected cattle should be displayed.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name8.Select Harit Pradesh Milk Producer Company Ltd.9.Click on Type field. 10. Select Type of the Cattle			8-01-2024	Selected cattle should be displayed.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
35	LOS	Loan Requirement Details	To Verify Cattle Required, ‘Breed’ field Should Visible and Clickable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name 8.Select Harit Pradesh Milk Producer Company Ltd.9.Click on Breed field.			8-01-2024	‘Breed’ field Should Visible and Clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
36	LOS	Loan Requirement Details	To Verify Selected Breed should be displayed.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name8.Select Harit Pradesh Milk Producer Company Ltd.9.Click on Breed field.			8-01-2024	Selected Breed should be displayed.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
37	LOS	Loan Requirement Details	To Verify Cattle Required, ‘Number’ field Should Visible and Clickable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name8.Select Harit Pradesh Milk Producer Company Ltd.9.Click on Number field.			8-01-2024	‘Number’ field Should Visible and Clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
38	LOS	Loan Requirement Details	To Verify Cattle Required, ‘Number’ field should be editable	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open.5.Click on Accept Button.6.Loan Requirement Page will Open. 7.Click on Dairy Society Name 8.Select Harit Pradesh Milk Producer Company Ltd.9.Click on Number field.10.Enter number in the field.			8-01-2024	‘Number’ field should be editable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
39	LOS	Loan Requirement Details	To Verify ‘Plus’ Button should be clickable.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Click on Dairy Society Name 8.Select Harit Pradesh Milk Producer Company Ltd. 9.Click on ‘Plus’ Button.			8-01-2024	User should be able to add other types of cattle.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
40	LOS	Loan Requirement Details	To Verify, Total Cost Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in Field. 8.Total Cost will be displayed.			8-01-2024	Total cost of the cattle should be visible	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
41	LOS	Loan Requirement Details	To Verify, Total Loan Amount Required.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in Field. 8.Total Loan Amount Field.			8-01-2024	Required loan amount field should be editable and user should be able enter loan amount.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
42	LOS	Loan Requirement Details	To Validate, Total Loan Amount Required.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in Field. 8.Enter Invalid Values or Keep field blank.			8-01-2024	Amount which is zero or more than cattle cost will not be accepted.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
43	LOS	Loan Requirement Details	To Verify,Insurance Company.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in Field. 8.Select Insurance Company from list.			8-01-2024	Insurance company name should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
44	LOS	Loan Requirement Details	To Verify,Loan Amount+Insurance Amount	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in Field. 8.Select Insurance Company from list. 9.Loan Amount+Insurance Amount will be displayed.			8-01-2024	Insurance amount + Loan Amount should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
45	LOS	Loan Requirement Details	To Verify,Bank Use Only Screen	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in Field. 8.Select Insurance Company from list. 9.Loan Amount+Insurance Amount will be displayed.10.Bank Use Only Screen.			8-01-2024	Bank use details should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
46	LOS	Loan Requirement Details	To Validate,RM Code Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.In Bank Use Only Screen in RM Code Field Enter Invalid Values or Keep field Blank.			8-01-2024	RM Code Field Should be editable and clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
47	LOS	Loan Requirement Details	To Validate,LG Code Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.In Bank Use Only Screen In LG Code Enter Invalid Values or Keep field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
48	LOS	Loan Requirement Details	To Validate,LC Code Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.In Bank Use Only Screen In LC Code Enter Invalid Values or Keep field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
49	LOS	Loan Requirement Details	To Validate,Distance from Branch Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.In Bank Use Only Screen In Distance From Branch Enter Invalid Values or Keep field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
50	LOS	Loan Requirement Details	To Validate,Distance from RM Location Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.In Bank Use Only Screen In Distance From RM Location Enter Invalid Values or Keep field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
51	LOS	Loan Requirement Details	To Verify,RO/SO Recommendation Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.In Bank Use Only Screen RO/SO Recommendation Field.			8-01-2024	System allows user to show and use RO/SO Recommendation Check Box Field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
52	LOS	Loan Requirement Details	To validate, RO/SO Recommendation Field	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.Keep blank the checkbox. RO/SO Recommendation Field.				System allows user to show and use RO/SO Recommendation Check Box should not be unmarked and error message should be shown.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
53	LOS	Loan Requirement Details	To Verify,Start Loan Application Button	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.Enter Values In Bank Use Only Screen 9.Click on Start Loan Application Button.			8-01-2024	System allows user to show and use Start Loan Application Button and Navigate to Personal Information Screen.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
54	LOS	Personal Information	To Verify,Personal Information Screen.	1.Open Dairy Loan URL in Browser. 2.Login Home page will open. 3.Login with OTP. 4.Pre-Approved Loan Details will open. 5.Click on Accept Button. 6.Loan Requirement Page will Open. 7.Enter Value in all Fields. 8.Enter Values In Bank Use Only Screen 9.Click on Start Loan Application Button.			8-01-2024	System allows user to show and use Start Loan Application Button and Navigate to Personal Information Screen.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
55	LOS	Personal Information	To Verify,Personal Information Screen.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open.			8-01-2024	System allows user to show and use Personal Information Screen with below details. - Account Details, - Location Details, - Additional Details.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
56	LOS	Personal Information	To Verify,Personal Information Screen.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open.			8-01-2024	System allows user to show and use Personal Information Screen with below details. - Account Details -Name,DOB,Gender, - A/c Number, - Education, - Branch Code, -Marital Status,	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
57	LOS	Personal Information	To Verify,Account Details	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open.			8-01-2024	System allows user to show and use Personal Information Screen with below details. - Account Details -Name,DOB,Gender, - A/c Number, - Education, - Branch Code, -Marital Status, - Address.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
58	LOS	Personal Information	To Verify,Location Details	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open.			8-01-2024	System allows user to show and use Personal Information Screen with below details. - Location Details - District, - Residence, - Type of Residence, - No. Of Years at Address. - Landmark.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
59	LOS	Personal Information	To Verify,District Drop down List.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	System allows user to show and use District drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
60	LOS	Personal Information	To Verify, Tehsil/Taluka Drop down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	User should be able to select Tehsil/Taluka from the list	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
61	LOS	Personal Information	To Verify, Village Drop down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	User should be able to enter village name in the field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
62	LOS	Personal Information	To Verify,Residence Drop down List.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	System allows user to show and use Residence drop down list. - , - Type of Residence, - No. Of Years at Address. - Landmark.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
63	LOS	Personal Information	To Verify,Type of Residence Drop down List.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	System allows user to show and use Type of Residence drop down list. - No. Of Years at Address. - Landmark.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
64	LOS	Personal Information	To Verify,No.Of Years at Address field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	System allows user to show and use No.Of Years at Address field .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
65	LOS	Personal Information	To Validate,No.of Years at Address field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.7.Enter Invalid Values or Keep Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
66	LOS	Personal Information	To Verify,Landmark field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.On Location Details Screen.			8-01-2024	System allows user to show and use Landmark Field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
67	LOS	Personal Information	To Verify, Additional Details	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details			8-01-2024	System allows user to show and use Additional Details Screen with below details. - Fathers Full Name , - Mothers Maiden Name - Religion, - Cast, - Vinatge In Dairy Firms (In Months).	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
68	LOS	Personal Information	To Verify, Fathers Full Name	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details			8-01-2024	System allows user to show and use Fathers Full Name field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
69	LOS	Personal Information	To Validate, Fathers Full Name	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Enter Invalid Values or Keep Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
70	LOS	Personal Information	To Verify, Mothers Maiden Full Name	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details			8-01-2024	System allows user to show and use Mothers Maiden Name field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
71	LOS	Personal Information	To Validate, Mothers Maiden Full Name	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Enter Invalid Values or Keep Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
72	LOS	Personal Information	To Verify, Religion Drop down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Select Religion From Drop down list.			8-01-2024	System allows user to show and use Religion Drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
73	LOS	Personal Information	To Verify, Cast Drop down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Select Cast From Drop down list.			8-01-2024	System allows user to show and use Cast Drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
74	LOS	Personal Information	To Verify, Vintage In Dairy Business(In Months) Field.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details			8-01-2024	System allows user to show and use Vintage In Dairy Business (In Months) field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
75	LOS	Personal Information	To Validate, Vintage In Dairy Business(In Months) Field.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Enter Invalid Values or Keep Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
76	LOS	Personal Information	To Verify, Additional KYC Screen	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Enter valid Values			8-01-2024	Additional KYC Screen should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
77	LOS	Personal Information	To Verify, ID Proof Drop Down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Enter valid Values 8. Click on ID Proof Drop Down Button 9. Enter Valid ID Proof Number in the Field.			8-01-2024	ID Proof Dropdown should be visible	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
78	LOS	Personal Information	To Verify, ID Proof No Field for Valid Input	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Additional Details. 7.Enter valid Values 8. Click on ID Proof Drop Down Button 9. Enter Invalid ID Proof Number in the Field.			8-01-2024	ID Proof accept Valid details	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
79	LOS	Personal Information	To Verify, Save & Continue Button.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button.			8-01-2024	System allows user to show and use Save & Continue button and after clicking it will Navigate to Land Details Page.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
80	LOS	Land Details	To Verify, Land Details Page.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Land Details Page with below details. -do you have Agriculture Land. Yes/No. - Back Button, - Continue Button. - Who Owns it. MySelf / Family Member.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
81	LOS	Land Details	To Verify, do you have Agriculture Land. If Yes	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Yes and Who Owns it. MySelf / Family Member.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
82	LOS	Land Details	To Verify, Who Owns it. If MySelf	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use below details if user has selected MySelf. - Survey No./Block No. - Land area (In Acres) – State, - District, -Tehsil , -Village ,	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
83	LOS	Land Details	To Verify, Survey No./Block No.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Survey no/Block No.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
84	LOS	Land Details	To Validate, Survey No./Block No.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open. 9.Enter Invalid Values or Keep Survey no./ Block No. Field			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
85	LOS	Land Details	To Verify, Land Area (acres)	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Land Area(Acres).	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
86	LOS	Land Details	To Validate, Land Area (acres)	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open. 9.Enter Invalid Values or Keep Land Area (acres) Field.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
87	LOS	Land Details	To Verify, State Drop Down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use State Drop down List.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
88	LOS	Land Details	To Verify, District Drop Down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use District drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
89	LOS	Land Details	To Verify, Tehsil Drop Down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Tehsil Drop down List.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
90	LOS	Land Details	To Verify, Village Drop Down List	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Village Drop down List.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
91	LOS	Land Details	To Verify, Who Owns it. If Family Member	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use below details if user has selected Family Member. - Name of the Land Owner, - Relationship with the applicant drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
92	LOS	Land Details	To Verify, Name of the Land Owner	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Name of the Land Owner,	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
93	LOS	Land Details	To Validate, Name of the Land Owner	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open. 9.Enter Invalid Values or Keep Name of the Land Owner Field.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
94	LOS	Land Details	To Verify, Relationship with Applicant Drop down list.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Personal Loan Information Screen will Open. 6.Fill all details in Location details,Additional Details & Verify Account Details. 7.Click on Save & Continue Button. 8.Land Details Page will be open.			8-01-2024	System allows user to show and use Relationship with Applicant drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
95	LOS	Land Details	To Validate, Land Area >=2	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Select Yes. 12.In MySelf Land Area. 13.enter area >=2 acer.			8-01-2024	System should allows user to Move on Income Tab.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
96	LOS	Land Details	To Validate, Land Area Owned land <0.5 Acres	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Select Yes. 12.In My Self Land Area. 13.enter area <0.5 acer.			8-01-2024	System should allows user to Show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
97	LOS	Land Details	To Validate,Family Member Land Area >=2	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Select Yes. 12.In Family Member Land Area. 13.enter area >=2 acer.			8-01-2024	System should allows user to Move on Income Tab.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
98	LOS	Land Details	To Validate, Land Area Family owned land <=2 Acres	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Select Yes. 12.In Family Member Land Area. 13.enter area <0.5 acer.			8-01-2024	System should allows user to Show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
99	LOS	Land Details	To Validate, Land Area >=2	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Select Yes. 12.In MySelf Land Area. 13.enter area >=2 acer.			8-01-2024	System should allows user to Move on Income Tab.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
100	LOS	Land Details	To Verify, do you have Agriculture Land. If No	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Select No. 12.Navigate to Income Tab.			8-01-2024	System should allows user to Navigate to Income Tab.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
101	LOS	Land Details	To Verify ,Back Button	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Click on Back Button.			8-01-2024	System should allows user to Navigate to Personal Information Tab.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
102	LOS	Land Details	To Verify ,Continue Button	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Click on Continue Button.			8-01-2024	System should allows user to Navigate to Income Tab.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
103	LOS	Land Details	To Verify,Geo Tagging	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Enter all Income Details. 12.Click on Geo Tagging Symbol.			8-01-2024	System Allows user to show and use Geo Tagging Symbol to add Land geo location.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
104	LOS	Land Details	To Verify, Geo Tag Land	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Enter all Income Details. 12.Click on Geo Tagging Symbol. 13.Geo Tag Land Pop-up will be Generated.			8-01-2024	System allows user to show and use Geo Tag Land Pop-up.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
105	LOS	Land Details	To Verify,Add Photo	1.Open URL in Browser. 2.Login with ETB Customer with Mobile Number. 3.Click on Customer ID and A/c Number Radio Button. 4.Click on Agree button. 5.Pre Approved cattle Loan pop-up will be displayed and click on accept. 6.Enter all details for Loan Requirements. 7.Start Loan Application. 8.Enter Personal Information. 9.Enter Land Details. 10.Do you have any Agricultural Land Yes/No. 11.Enter all Income Details. 12.Click on Geo Tagging Symbol. 13.Geo Tag Land Pop-up will be Generated. 14.Click on Add Photo and Continue.			8-01-2024	System Allows user to show and use Add photo Button to Capture Land Image.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
106	LOS	Income Details	To Verify, Income Page.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open.			8-01-2024	System allows user to show and use Income Details Page with below details. - Additional Income, - Existing Cattle.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
107	LOS	Income Details	To Verify,Existing Cattle Type Drop down list	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open.			8-01-2024	System allows user to show and use Type Drop down List	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
108	LOS	Income Details	To Verify, Number Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open.			8-01-2024	System allows user to show and use Number Field	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
109	LOS	Income Details	To Validate, Number Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Invalid Values or Keep Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
110	LOS	Income Details	To Verify, ‘Plus’ Button should be clickable	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Click On ‘Plus’ Button.			8-01-2024	System allows user to show and use Income per Annum Field	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
111	LOS	Income Details	To Verify, Dairy Income per Annum Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
112	LOS	Income Details	To Validate, Income per Annum Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Invalid Values or Keep Income per Annum Field Blank.			8-01-2024	System allows user to show and use Agriculture Income per Annum Field	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
113	LOS	Income Details	To Verify, Agriculture Income per Annum Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
114	LOS	Income Details	To Validate, Agriculture Income per Annum Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Invalid Values or Keep Agriculture Income per Annum Field Blank.			8-01-2024	System allows user to show and use Other Income Field	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
115	LOS	Income Details	To Verify,Other Income Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
116	LOS	Income Details	To Validate, Other Income Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Invalid Values or Keep Other Income Field Blank.			8-01-2024	System allows user to enter amount > 2.5 Lack and also ask for PAN Card Details.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
117	LOS	Income Details	To Validate, If Other Income >250000	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field.			8-01-2024	System allows user to show and use Do you Have PAN? Yes/No.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
118	LOS	Income Details	To Verify, Do you Have PAN? Yes/No.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field.			8-01-2024	System allows user to show and use PAN Card Field..	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
119	LOS	Income Details	To Verify, Do you Have PAN? If Yes .	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.PAN Card Field will be displayed.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
120	LOS	Income Details	To Validate, PAN Card Field .	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Enter Invalid Values or Keep PAN Card Field Blank.			8-01-2024	System allows user to show and use Have you Applied for PAN Card? Yes/No.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
121	LOS	Income Details	To Verify, Do you Have PAN? If No .	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/no.			8-01-2024	System allows user to show and use below details. -Application Acknowledgement, - Application Date.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
122	LOS	Income Details	Have you Applied for PAN Card? If Yes	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/no.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
123	LOS	Income Details	Have you Applied for PAN Card? If No	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/no.			8-01-2024	System allows user to show and use Application Acknowledgement.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
124	LOS	Income Details	To Verify, Application Acknowledgement	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/No. 11.Have you Applied for PAN Card? If Yes			8-01-2024	System allows user to show and use Application Acknowledgement.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
125	LOS	Income Details	To Valid, Application Acknowledgement	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/No. 11.Have you Applied for PAN Card? If Yes 12.Enter Invalid Values or Keep Application Acknowledgement Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
126	LOS	Income Details	To Verify, Date of Application	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/No. 11.Have you Applied for PAN Card? If Yes			8-01-2024	System allows user to show and use Date of Application.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
127	LOS	Income Details	To Valid, Date of Application	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/No. 11.Have you Applied for PAN Card? If Yes 12.Enter Invalid Values or Keep Date of Application Field Blank.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
128	LOS	Income Details	To Verify, Continue	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open. 9.Enter Amount >2.5 lack in Other Income Field. 10.Have you Applied for PAN Card? Yes/No. 11.Have you Applied for PAN Card? If Yes 12.Click on Continue Button.			8-01-2024	System allows user to Navigate to Eligibility Screen	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
129	LOS	Eligibility Details	To Verify, User Should be navigate to Eligibility Screen	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button.			8-01-2024	System allows user to show and use Eligibility Screen with below details. -Congrats Message – Sanctioned Loan Amount, - Loan Tenure, EMI, Repayment, Processing Fee, - Checkbox to Agree, - Accept & Continue Button.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
130	LOS	Eligibility Details	Verify that, I agree to hypothecations of my cattle ‘Check Box’ should be visible and clickable.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
131	LOS	Eligibility Details	Verify that,”I’ll do it later” text should be visible and clickable.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on ”I’ll do it later” text.			8-01-2024	I’ll do later text should be visible	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
132	LOS	Eligibility Details	Verify that, ‘Accept and Continue’ Button should be disabled.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button.			8-01-2024	Accept and Continue button should be disabled.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
133	LOS	Eligibility Details	Verify that, ‘Accept and Continue’ Button should be clickable when check box is marked.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’			8-01-2024	Check box should be clickable and ‘Accept and Continue’ button should be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
134	LOS	Eligibility Details	Verify that, User should be navigate to next page when clicked on “I’ll do it later”	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on ”I’ll do it later” text.			8-01-2024	User should be navigate to next page.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
135	LOS	Eligibility Details	Verify that, Detailed Charges Pop up Should be visible.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’			8-01-2024	Pop UP should be visible.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
136	LOS	Eligibility Details	Verify that Cancel Button should be clickable on Pop up.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’ 16. Click on ‘Cancel’ button.			8-01-2024	Cancel button should be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
137	LOS	Eligibility Details	To Verify, Hold EMI Every Month On Drop Down List.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’ 16.Click on Hold EMI every month drop down button.			8-01-2024	Hold EMI drown should be clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
138	LOS	Eligibility Details	To Verify, Selected date should be visible in the field.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’ 16.Click on Hold EMI every month drop down button. 17. Select Date from the drop down.			8-01-2024	User should be able to select date.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
139	LOS	Eligibility Details	To Verify, Submit Button should be disabled if the date is not selected.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’			8-01-2024	Submit button should be disabled if date is not selected.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
140	LOS	Eligibility Details	To Verify, ‘Plus’ button should be clickable.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’ 16.Click on Hold EMI every month drop down button. 17. Select Date from the drop down.			8-01-2024	Plus button should be clickable	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
141	LOS	Eligibility Details	To Verify, Cancel Button Should be Clickable	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’ 16.Click on Hold EMI every month drop down button. 17. Select Date from the drop down. 18.Click on ‘Cancel’ Button			8-01-2024	Cancel button should be clickable.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
142	LOS	Eligibility Details	To Verify, Submit Button should be Clickable if the date is selected.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Liablities Screen. 10.Click on ‘Add Liabilities’ button 12. Add Loan Details 13. Click on Continue button. 14. Click on I agree to hypothecations of my cattle ‘Check Box’ 15. Click on ‘Accept And Continue button’ 16.Click on Hold EMI every month drop down button. 17. Select Date from the drop down.			8-01-2024	System allows user to Navigate to Declaration Screen	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
143	LOS	Declaration	To Verify, Declaration Screen	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open.			8-01-2024	System allows user to Navigate to Declaration Screen with below details. - Declare EMI Holding Date.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
144	LOS	Declaration	To Verify, Consent For Transfer into Loan Account Number.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue.			8-01-2024	System allows user to Show and use Hold EMI Every Month on Drop down list.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
145	LOS	Declaration	To Verify, General Insurance Document.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue.			8-01-2024	System allows user to Show and use Submit Button and will Show T&C.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
146	LOS	Declaration	To Verify, Most Important Terms and Conditions & Declaration By Customer.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue.			8-01-2024	System allows user to Show the Condition and able to Accept and Continue to Navigate to Next Condition.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
147	LOS	Declaration	To Verify, Acknowledgement	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue.			8-01-2024	System allows user to Show the Condition and able to Accept and Continue to Navigate to Next Condition.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
148	LOS	Declaration	To Verify, Relationship Declaration.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue.			8-01-2024	System allows user to Show the Condition and able to Accept and Continue to Navigate to Next Condition.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
149	LOS	E- Sing	To Verify, e-Sign Screen	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open.			8-01-2024	System allows user to Show and use eSign Page with below details. - Document Acceptance - Sanction Letter , - Form 60, - Loan Agreement.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
150	LOS	E- Sing	To Verify, Sanction Letter	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open.			8-01-2024	System allows user to Show and use Sanction Letter Click on it and Accept it.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
151	LOS	E- Sing	To Verify, Form 60	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open.			8-01-2024	System allows user to Show and use Form 60 Click on it and Accept it.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
152	LOS	E- Sing	To Verify, Loan Agreement	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open.			8-01-2024	System allows user to Show and use Loan Agreement Click on it and Accept it.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
153	LOS	E- Sing	To Verify, eSign Button	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.			8-01-2024	System allows user to Show and use eSign Button Click on it and will Navigate to Login to HDFC Bank Debit/ATM Card Verification Page.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
154	LOS	E- Sing	To Verify, Debit Card Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button.			8-01-2024	System allows user to Show and use Debit Card Field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
155	LOS	E- Sing	To Validate, Debit Card Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Enter Invalid Values or Keep Debit Card field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
156	LOS	E- Sing	To Verify, Timeout Session.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button.			8-01-2024	System allows user to Show and use 5 min Timeout Session.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
157	LOS	E- Sing	To Validate, Timeout Session.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button.			8-01-2024	System allows user to Session will Expire after 5 Min.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
158	LOS	E- Sing	To Verify, Expiry Date Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button.			8-01-2024	System allows user to Show and use Expiry Date Field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
159	LOS	E- Sing	To Validate, Expiry Date Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Enter Invalid Values or Keep Expiry Date field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
160	LOS	E- Sing	To Verify, PIN Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button.			8-01-2024	System allows user to Show and use PIN Field.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
161	LOS	E- Sing	To Validate, PIN Field	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Enter Invalid Values or Keep PIN field Blank.			8-01-2024	System allows user to show Valid Message.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
162	LOS	E- Sing	To Verify, T&C Checkbox	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.			8-01-2024	System allows user to Show and use T&C Checkbox to Accept it.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
163	LOS	E- Sing	To Validate, T&C Checkbox	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.21.Dont Select Checkbox for T&C.			8-01-2024	System allows user to show Valid Message .	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
164	LOS	E- Sing	To Verify, Click Here Button.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.21.Click on Click Here button.			8-01-2024	System allows user to show and use Click button to see TnC in Details.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
165	LOS	E- Sing	To Verify, I Agree Button.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.21.Click on Click Here button.			8-01-2024	System allows user to show and use I Agree Button to accept TnC Conditions.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
166	LOS	E- Sing	To Verify, I disagree Button.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.21.Click on Click Here button.			8-01-2024	System allows user to show and use I disagree Button to reject TnC Conditions.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
167	LOS	E- Sing	To Verify, Continue Button.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.21.Click on Continue button.			8-01-2024	System allows user to show and use All Done Page with below details. - Loan Amount, - Loan Application No. - Sanction Letter, - Form 60, - Loan Agreement.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe
168	LOS	E- Sing	To Verify, Cancel Button.	1.Open Dairy Loan URL in Browser. 2.Login with Mobile Number and OTP. 3.Fill Loan Requirement Details. 4.Click on Start Loan Application Button. 5.Fill Personal Loan Information & Land Details. 7.Click on Save & Continue Button. 8.Income Page will be open & Fill all Details. 9.Verify Elegibility Screen. 14.Click on Accept&Continue Button. 15.Declaration Screen will Open. 16.Enter details on it and Continue. 17.eSign Page will be Open. 18. Accept all Documents.19.Click on eSign Button. 20.Login to HDFC Bank Screeen will Open.21.Click on Cancle button.			8-01-2024	System allows user to show and use Cancel button.	Working As Expected	Pass	12-02-2024							Pratik Ubhe	Pratik Ubhe